## Summary
Fee Reconciliation Workbench — Retest Report
Intellipaat PM assignment prototype · retested and security-reviewed 27 Oct 2026 · Yasin Jariwala
Bugs found | 14 | All bugs logged on the Bug Log sheet
Bugs fixed | 14 | Change Status on Bug Log to update
Bugs open | 0
By severity
Crash | 3 | Page stopped working
Money | 4 | Could miscount money or hide a bank-data conflict
Control | 1 | Weakened a financial control
Matching | 1 | Missed a valid link
Workflow | 1 | No way to finish a task
Display | 3 | Showed misleading information
Usability | 1 | Harder to use
Live scenarios | 27
Failed on first run | 13 | Includes failures cascading from earlier crashes
Passing on final run | 27 | Run on the published page and the standalone file
Final pass rate | 100%
Random stress-test actions | 72000 | No invariant violations after fixes
In-app QA tests passing | 25
Security checks run | 17
Security findings fixed | 11 | High-risk findings shown on the Security Review sheet
Security checks passed first time | 6
Security findings open | 0
Green numbers link to other sheets. Edit the Status column on Bug Log and the counts update.

## Bug Log
Bug ID | What went wrong | Severity | How it was found | Root cause | Fix | Retest coverage | Status
BUG-01 | Page crashed when the bank re-sent a reversal and its detail was opened | Crash | Live scenario S04 | Reversal panel assumed every reversal record had reversal data; duplicates do not | Duplicate records skip the reversal and candidate panels | S04, TC-12 | Fixed
BUG-02 | Allocation form crashed after Reject, Verify cash or Retry student lookup | Crash | Live scenarios S10, S11 | Editor state was cleared after the page re-rendered, leaving a form with no state behind it | Editor re-initialises whenever the payment changes; handlers guard against missing state | S03, S10, S11 | Fixed
BUG-03 | Reset crashed when signed in as a student registered during the demo | Crash | Live scenario S14 | Reset removed the student but kept the signed-in role | Reset falls back to Operations if the signed-in student no longer exists | S14 | Fixed
BUG-04 | Same bank ID with a different amount was silently filed as a harmless duplicate | Money | Random stress test | Duplicate check compared IDs only, and copied the original record type | New "Same ID, different amount" status; adds no money; only Finance can close it with a note | S26, TC-19 | Fixed
BUG-05 | Bank ID with lower case or spaces slipped past the duplicate check | Money | Live scenario S07 | Exact string comparison of transaction IDs | IDs normalised (case, spacing, punctuation, digit-only match for 10+ digits) | S07, TC-19 | Fixed
BUG-06 | A reversal could attach to P4 (a duplicate) or to cash | Money | Live scenario S05 | Remark lookup accepted any record ID | Reversals only link to real, non-duplicate bank payments; otherwise exception with reason | S05, TC-22 | Fixed
BUG-07 | A positive credit with a reversal reference was treated as a reversal | Money | Live scenario S06 | Reversal decided by reference field, not by sign of amount | Only negative amounts are reversals; positive ones become payments with a warning flag | S06, TC-22 | Fixed
BUG-08 | Two students claiming the same payment both showed as strong matches | Control | Live scenario S09 | Each claim added its own High candidate with no conflict check | Both downgraded to Medium; conflict flagged; also flags claims on money allocated to someone else | S09, TC-21 | Fixed
BUG-09 | UTR typed as plain digits never linked to the bank record | Matching | Live scenario S08 | Claim UTR compared exactly with formatted bank ID | Same ID normalisation used for claim linking and re-checks | S08, TC-20 | Fixed
BUG-10 | Reversal exceptions stayed in the queue forever with no way to close them | Workflow | Live scenario S15 | No close or re-link action existed | Finance approver can re-check the link or close without applying (note required, audited) | S15, TC-22 | Fixed
BUG-11 | Blocked reversal still previewed its effect (e.g. ₹10,000 → −₹2,000) | Display | Screenshot review | Impact preview shown for every non-applied state | Preview only while awaiting approval; exceptions show the unchanged amount | Visual check | Fixed
BUG-12 | Student still told "being allocated" after the payment was posted | Display | Live scenario S21 | Claim status ignored allocations on the linked bank record | Shows "Received and recognised" with the posted amount | S21 | Fixed
BUG-13 | Books check said it included student claims but left out P7 | Display | Live scenario S22 | Unverified total counted cash only | Unverified total includes claims not yet found in the bank | S22 | Fixed
BUG-14 | Queue rows not keyboard-reachable; simulator reopened on last-used tab | Usability | Live scenarios S23, S15 | Rows lacked tabindex; tab state persisted | Rows focusable with Enter to open; simulator always opens on Bank feed | S23, S15 | Fixed

## Live Scenarios
Scenario | What was tested | First run | Bug(s) found | Final run
S01 | Ops matches P1 → Admission; Ops cannot approve; Finance approves; ledger + receipt | Pass |  | Pass
S02 | P6 split through the UI, approved, money counted once | Pass |  | Pass
S03 | Finance rejects a proposal, Ops re-proposes straight away | Pass |  | Pass
S04 | Bank re-sends the P8 reversal; open its detail page | Fail | BUG-01 | Pass
S05 | Reversal whose remark points at duplicate P4 | Fail | BUG-06 | Pass
S06 | Positive amount wrongly tagged with a reversal reference | Fail | BUG-07 | Pass
S07 | Re-import of P1 with different formatting (lower case, spaces) | Fail | BUG-05 | Pass
S08 | Student types UTR digits only; bank credit arrives later | Fail | BUG-09 | Pass
S09 | Two students claim the same UTR | Fail | BUG-08 | Pass
S10 | Payment before registration → sync → retry → allocate | Fail | BUG-02 | Pass
S11 | Cash P5: counsellor evidence → counsellor cannot verify → Finance verifies → allocate | Fail | BUG-02 | Pass
S12 | Student-system timeout → retry twice → one entry | Pass |  | Pass
S13 | Wrong allocation corrected, then re-allocated correctly | Pass |  | Pass
S14 | Reset while signed in as a late-registered student | Fail | BUG-03 | Pass
S15 | Oversized second reversal on P3 goes to exception and can be closed | Fail | BUG-10, BUG-14 | Pass
S16 | Deep links to missing records | Pass |  | Pass
S17 | Every view renders for every role | Pass |  | Pass
S18 | Phone width: no sideways page scroll on any view | Pass |  | Pass
S19 | Admin turns on AA-1, resets; P1 and P3 auto-post | Pass |  | Pass
S20 | Overpayment needs an approval note | Pass |  | Pass
S21 | Student view shows a linked + posted claim as recognised | Fail | BUG-12 | Pass
S22 | Books check card counts the student claims it says it counts | Fail | BUG-13 | Pass
S23 | Queue keyboard access | Fail | BUG-14 | Pass
S24 | Search, filters and audit filter while typing | Pass |  | Pass
S25 | Two proposals pending, reversal tries to over-commit | Pass |  | Pass
S26 | Same bank ID re-sent with a different amount (added after stress test) | Not in first run | BUG-04 | Pass
S27 | Run the in-app QA suite from the Engineering page (added in retest) | Not in first run |  | Pass
Note: some first-run failures (S15, S18–S25) partly cascaded from earlier crashes in the same browser session; the "Bug(s) found" column lists only genuine defects.

## Test Methods
Method | What it covers | Volume | Pass criteria
Live browser scenarios | Scripted clicks and typing in a real browser across Operations, Counsellor, Finance reviewer, Finance approver, Admin and each student | 27 | After every step: control difference ₹0, no duplicate receipt or ledger entry, no over-allocated payment, no page errors
Phone-width check | Every page and the simulator at 390px wide | 12 views + modal | No sideways page scroll
Random stress test | Random actions by random roles on the rules engine (3 seeds × 60 runs × 400 steps) | 72000 | Books balance; nothing reversed beyond receipt; no self-approval; no ledger entry from unverified money; no two live records with one bank ID
In-app QA suite | Automated checks on the Engineering and QA page, mapped to acceptance criteria | 25 | All passing (18 original + 4 regression TC-19 to TC-22 + 3 security TC-23 to TC-25)
Security attack suite | XSS in every text field, link tampering, student data leaks, UTR probing, claim hijack, separation of duties, input abuse, least privilege, network and storage | 20 | 0 findings open on published page and standalone file
Visual review | Screenshots of ledger, queue and reversal-exception screens | 3 | Layout and wording correct

## Security Review
ID | Area | Finding / check | Risk | Fix or result | Status
SEC-01 | Data leak | Student could see college-wide finance totals (verified, posted, pending, unallocated) on the Start page | High | Totals shown to staff only; students see a link to their own ledger | Fixed
SEC-02 | Probing | Student could test any UTR and the screen confirmed "Found in bank records", revealing other people's payments | High | Students only ever see "Under review" until money is allocated to them | Fixed
SEC-03 | Claim hijack | Student S102 could claim P1 (bank reference names S101) and became an equal High-confidence candidate | High | A claim can never outrank the bank reference; disputed claim set to Low and flagged | Fixed
SEC-04 | Separation of duties | One Finance approver could approve an allocation and then reverse it alone | High | Corrections are two-person: request by one, approval by a different Finance approver | Fixed
SEC-05 | Impersonation | Staff could file a mismatch case with no student behind it | Medium | Only a signed-in student can raise a case, for themselves; attempts are audited | Fixed
SEC-06 | Abuse / flooding | A student could submit unlimited payment claims | Medium | Maximum 5 claims (and 5 open cases) under review per student | Fixed
SEC-07 | Input validation | Implausible amounts (e.g. ₹1,000 trillion, text, blank ID) were accepted as payments | Medium | Rejected at import and audited; limit ₹10 crore per event | Fixed
SEC-08 | Input validation | Free text was unbounded (100,000-character case accepted) | Low | All text fields clipped (IDs 64, names 120, notes 1,000 characters) | Fixed
SEC-09 | Least privilege | Counsellors and Operations could read the full audit log, including evidence notes for all students | Medium | Audit log limited to Finance reviewer, Finance approver and Admin | Fixed
SEC-10 | Robustness | Links like #constructor or #__proto__ broke the page | Low | Only known page names are routed; anything else opens the Start page | Fixed
SEC-11 | Hardening | Standalone file had no Content-Security-Policy | Medium | Strict policy added: no network calls, no outside scripts, no forms, no plugins; fonts only from Google Fonts | Fixed
SEC-12 | Code injection (XSS) | Script payloads typed into 25 text fields, shown on every screen and role | — | All output escaped; nothing executed | Passed
SEC-13 | Access control | Student opening another student's ledger or staff screens by link | — | Forced to own ledger | Passed
SEC-14 | Data leak | Student seeing other students' receipts | — | Only own receipts shown | Passed
SEC-15 | Network | Any outbound calls (fetch, XHR, WebSocket, beacon) or eval | — | None; only Google Fonts | Passed
SEC-16 | Storage | Data written to cookies, localStorage or sessionStorage | — | None | Passed
SEC-17 | File handling | Uploaded screenshot contents read or sent anywhere | — | Only the file name is read; file never leaves the browser | Passed
Scope: this is a browser prototype. Roles are switched freely for demonstration and all rules run in the page. In production every permission and limit above must be enforced on the server, behind real sign-in.